PYMBLE CONSTRUCTION LIMITED

Engineering

Operations Workbook

Getting the work built right, and leaving a record good enough to prove it was.

| For | Engineering Manager · Engineer · Engineering Intern |
| --- | --- |
| Covers | 36 modules you can open |
| Version | 1.0 |
| Issued | 19 August 2026 |

Internal document. Access shown here is taken from the system's own role matrix.

Contents

To fill in the page numbers: click anywhere in the contents, then press F9.

# 1. How to use this workbook

This is the Engineering edition. It covers only the modules your roles can actually open, so nothing in it is somebody else's job.

## How each module is described

- What it is for — one sentence.

- How it moves — the states a record passes through, where the module is a workflow.

- How to operate it — the instructions.

- What happens if you don't — the consequence of skipping a step. This is the part most people need.

## Two words used precisely

Live — the record is governing something. A live budget controls spend. A draft one does not, no matter what is written on it.

Charged — money has been attached to a specific piece of work. Money that is not charged still exists; it just cannot be reported against anything.

If you take one thing from this workbook Almost every problem in this system comes from a step that was started and not finished — prices attached but never sent, a budget written but never activated, an order approved but never issued. Each of these now shows on a screen. Nothing here asks you to remember anything.

# 2. What your department can open

Your roles can open 36 of the system's 79 modules. Everything else is another department's, and you will not see it in the menu.

Access differs between roles within the department. This table is the definitive list.

| Module | Engineering Manager | Engineer | Engineering Intern |
| --- | --- | --- | --- |
| Overview | Yes | Yes | — |
| Projects and Sites | Yes | Yes | — |
| My Sites | — | — | Yes |
| Workers | Yes | Yes | — |
| Attendance | Yes | Yes | Yes |
| Approval Rules | Yes | Yes | — |
| Approvals | Yes | Yes | — |
| Notifications | Yes | Yes | — |
| My Conversations | Yes | Yes | — |
| Material Schedule | Yes | Yes | — |
| Invoices | Yes | Yes | — |
| Photos | Yes | Yes | — |
| Documents | Yes | Yes | Yes |
| Modules | Yes | Yes | — |
| Glossary | Yes | Yes | — |
| Settings | Yes | Yes | — |
| Daily Site Reports | Yes | Yes | Yes |
| Material Requests | Yes | Yes | — |
| Site Instructions and Quality Assurance / Quality Control | Yes | Yes | — |
| Site Checklists | Yes | Yes | — |
| Project Schedule and Progress | Yes | Yes | — |
| Stores and Inventory | — | Yes | — |
| Delivery Exceptions | — | Yes | — |
| Cost Codes and WBS | Yes | — | — |
| Equipment | Yes | Yes | — |
| Fleet and Logistics | Yes | Yes | — |
| Incidents and Actions | Yes | Yes | — |
| Health, Safety and Environment Compliance | Yes | Yes | — |
| Weekly Health, Safety and Environment Report | Yes | Yes | — |
| Interim Payment Certificates, Variations and Claims | — | Yes | — |
| Subcontractors | Yes | Yes | — |
| Contracts | Yes | Yes | — |
| Department Reports | Yes | Yes | — |
| Engineering Reports | Yes | Yes | — |
| Get IT Help | Yes | Yes | Yes |
| IT Policies & Guides | Yes | Yes | Yes |

If you cannot see something you think you should Access is set per role, and can be adjusted by IT for anything that is not a money or people module. Ask your manager first — the usual answer is that the work belongs to another role.

# 3. Procurement and materials

## 3.1 Material Schedule

YOUR DEPARTMENT OWNS THIS

What it is for. The list of everything a project is planned to consume, with quantities. It is what makes planned-versus-actual possible.

### How it moves

- Draft — Quantity Surveyor, Engineer or Projects Manager writes the schedule and its lines

- Pricing pending — Submitted to Procurement

- Priced — Procurement has attached unit rates and transport estimates

- Issued — Locked in — and this is what generates the project budget

### How to operate it

- Give each line a description, unit, quantity and a cost code. The cost code is what lets material requests inherit the right charge.

- Procurement prices the schedule, not Engineering. Engineering owns the quantities; Procurement owns the rates.

- Issuing generates or updates the site's project budget, one budget line per category, inheriting the cost code from the schedule lines it was summed from.

- A revision supersedes the previous schedule rather than deleting it. Categories the revision no longer covers are zeroed, not removed, because spend may already reference them.

- Material requests match against schedules that are priced OR issued, so a schedule still with Procurement already helps requests charge correctly.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| No schedule is created for a site | Every request on that site charges contingency. Variance reporting is impossible — the system can tell you how much was spent but not what on. |
| A schedule is drafted but never priced | Requests can still match against it once priced, but no budget is generated. |
| A schedule is priced but never issued | No project budget is created. Issuing is what generates it. |
| A schedule line has no cost code | Requests matching that line inherit nothing and fall through to contingency. |

## 3.2 Delivery Exceptions

What it is for. Recording when a delivery was late, short, over, damaged or wrong, so the supplier record reflects it.

### How it moves

- Open

- Investigating

- Resolved

- Closed

### How to operate it

- Raise the exception when the delivery is received, not later. Types are late, short, over, damaged, wrong item, and quality.

- Severity is low, medium, high or critical — it drives who is notified.

- Resolving an exception is a statement that the matter is settled with the supplier, not that time has passed.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Exceptions are not raised | Supplier performance looks perfect on paper. The register cannot tell you who is reliable, which is the only reason to keep it. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| An open exception | 2 days |

## 3.3 Material Requests

What it is for. Getting materials to a site, with the company knowing what was ordered, what it cost, and which work it was for.

### How it moves

- Draft — Requester builds the request and adds line items

- Submitted — Sent for approval

- Operations approved — Projects Manager, then Operations Manager

- Pricing — Procurement attaches the actual supplier prices

- Priced — Procurement sends it to Finance

- Cost approved — Finance Manager or Accountant approves the money

- Ordered — Procurement raises and issues the purchase order

- Delivered — Requester or site manager confirms the goods arrived

- Closed — Stores, or automatically on full delivery

### How to operate it

- Add every line item before submitting — a request with no lines cannot be submitted.

- Name the supplier on each line. Pick one from the register if they are on it; type the name if they are not.

- You do not need to pick a cost code. The system derives it: your choice first, then the material schedule line the item matches, then the request's budget line, then the site's unplanned / contingency budget.

- Site requests under K25,000 go Projects Manager then Operations Manager. K25,000 and over adds the Managing Director. Office and general requests go to the Operations Manager only.

- If there is no active Projects Manager, the Managing Director covers that step.

- Requests marked IT are confidential and visible only to leadership, IT, Procurement and Finance.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| No supplier is named on any line | The request cannot be sent to Finance. The screen says so from the moment you add items — you do not have to wait until you press Send. |
| The supplier is typed rather than picked from the register | Still blocked, but the cheap fix is to add them to the supplier register. Recording comparison prices also clears it. |
| The request is K1,000,000 or more | Comparison prices are the only way through. Use Record comparison prices on the request itself. |
| No cost code can be derived | The spend charges unplanned / contingency, so it will not appear against the work it was actually for. That usually means the item is not on the site's material schedule. |
| Procurement prices it but never presses Send to Finance | The request sits in Pricing indefinitely. This is the most common way a request goes quiet. |
| Finance approves but nobody raises the purchase order | The money is reserved but never committed. The budget looks more spent than it is, and the site never gets the goods. |
| The purchase order is raised but never issued | Same as above. A draft order is not an order. |
| Delivery is never confirmed | The cost never becomes actual, so it never reaches the accounts. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| Waiting for approval | 2 days |
| Waiting for pricing | 2 days |
| Approved but not ordered (a reservation) | 60 days, or as soon as the needed-by date is 30 days past |

## 3.4 Stores and Inventory

What it is for. What the company physically holds, where it is, and what has moved in or out.

### How it moves

- Goods received note — Recorded against a purchase order line when the delivery arrives

- Stock movement — Receipt, issue, transfer or adjustment

- Purchase order closes — Once everything ordered has been received

### How to operate it

- Locations are central store, site store, yard, or vehicle. Every movement is between locations.

- A goods received note is the receipt evidence for a delivery, and the basis of the three-way match between order, receipt and invoice.

- Receipting in full closes the purchase order and the material request behind it.

- An adjustment records a stock count difference — use the reason field, because an unexplained adjustment is indistinguishable from a loss.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| No goods received note is recorded | Delivery is confirmed on somebody's word alone. The three-way match has nothing to work with, and an overcharge on the supplier invoice cannot be caught. |
| Issues to site are not recorded | Stock on hand is overstated, and the site appears not to have received material it is using. |

# 4. Engineering and site control

## 4.1 Daily Site Reports

YOUR DEPARTMENT OWNS THIS

What it is for. What happened on site each day — progress, labour, plant, materials, delays, safety and commercial events.

### How it moves

- Draft

- Submitted

- Reviewed

- Closed

### How to operate it

- One report per site per day. Entries are typed: progress, labour, equipment, material, delay, HSE, commercial.

- Record delays on the day they happen with the reason. A delay reconstructed weeks later is worth very little in a claim.

- Reports can be written offline and sync when there is signal.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Daily reports are not written | There is no contemporaneous record of delay or disruption. Extension-of-time and loss-and-expense claims depend almost entirely on this. |

## 4.2 Site Instructions and Quality Assurance / Quality Control

YOUR DEPARTMENT OWNS THIS

What it is for. Site instructions, quality inspections, material tests, snags and the drawing register.

### How it moves

- Site instruction: draft → issued → acknowledged → closed

- Inspection: planned → completed → action required → closed

- Snag: open → in progress → resolved → verified

### How to operate it

- A site instruction is a formal direction. Issue it, and get it acknowledged — an unacknowledged instruction is a conversation, not an instruction.

- Inspections record a result per item: pass, fail, observation, or not applicable. A fail creates a finding with a category.

- Material tests run scheduled → submitted → passed or failed.

- Drawings are current, superseded or archived. Superseding is how you stop people building from an old sheet.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An instruction is issued but never acknowledged | There is no proof the site received it. |
| A snag is resolved but never verified | Nobody has confirmed the fix. Verification is a separate step for a reason. |
| A drawing revision is not superseded | Two current versions of the same drawing exist, and somebody will build from the wrong one. |

## 4.3 Site Checklists

YOUR DEPARTMENT OWNS THIS

What it is for. Structured checks at the points where work must not proceed unchecked.

### How to operate it

- Templates are fixed in code so a checklist means the same thing on every site.

- Hold points can be overridden where circumstances require it, and the override is recorded.

- The Project Manager sign-off gate cannot be overridden.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A checklist is skipped | The hold point it protects was never checked, and there is no record of who decided to proceed. |

## 4.4 Project Schedule and Progress

YOUR DEPARTMENT OWNS THIS

What it is for. The programme: tasks, milestones and progress against plan.

### How to operate it

- Milestones carry a status — planned, on track, at risk, and so on.

- Tasks can carry a cost code, which links the programme to the money.

- Overdue tasks escalate automatically.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| The programme is not maintained | Progress reporting becomes opinion, and slippage is discovered rather than predicted. |

## 4.5 Engineering Reports

What it is for. Your department's own weekly report and its history.

### How to operate it

- Write it from what the system already holds rather than from memory — the figures are there.

- The manager compiles the department report from the contributors' submissions.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| The report is skipped | Leadership sees no position for your department that week, and reminders continue on Monday and Tuesday. |

# 5. Your day

## 5.1 Approval Rules

What it is for. The thresholds and chains that decide who approves what.

### How to operate it

- The material request threshold is K25,000 — above it the Managing Director is added as a final step.

- The competitive tender threshold is K1,000,000 — at or above it, recorded comparison prices are the only way through.

- Budget bands: warn at 90%, record-why at 100%, escalate at 110%.

- Raising a threshold can only ever shorten a chain, so change it deliberately.

## 5.2 Approvals

What it is for. Everything waiting for your decision, in one place.

### How to operate it

- An approval has ordered steps. Yours becomes actionable when the steps before it are done.

- A rejection needs a reason. The requester sees it and acts on it.

- Cancelling the underlying record withdraws its approval automatically — you will not be asked to authorise something that no longer exists.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An approval is left sitting | Everything behind it stops. Approvals are flagged as late after 2 days and then escalate. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| Any approval step | 2 days |

## 5.3 Get IT Help

What it is for. Raising an IT problem.

### How to operate it

- Describe what you were doing when it happened. A ticket saying 'it does not work' takes three messages to become useful.

## 5.4 My Conversations

What it is for. Conversations and mentions on records.

### How to operate it

- Mentioning someone notifies them and links them to the record in question.

## 5.5 My Sites

What it is for. The sites you are assigned to, with field shortcuts.

### How to operate it

- This is the site-team home: attendance, daily reports and photos in one place, and it works offline.

## 5.6 Notifications

What it is for. What the system needs you to know about.

### How to operate it

- Notifications are deduplicated, so a repeated event updates the existing notice rather than adding another.

- An action link takes you straight to the record.

# 6. Projects and people

## 6.1 Attendance

What it is for. Who was on site, on which day.

### How to operate it

- Pay is a fixed daily rate for each attended day — K60 flat — plus separately entered overtime. Base pay is never scaled by hours worked.

- Presence is present, late, or absent.

- Attendance can be captured in the app or entered manually, and works offline on site.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A day is not captured | That worker is not paid for it. Payroll builds only from what attendance recorded. |

## 6.2 Contracts

What it is for. Works orders and employment contracts, from drafting through signature.

### How it moves

- Draft

- Review

- Approved

- Sent for signature

- Signed / active

- Completed or terminated

### How to operate it

- Contracts are built from a standard template, then every clause can be edited per contract.

- Two template kinds: works order (for a supplier or subcontractor) and employment.

- Signatures are rendered server-side onto the document — the signed PDF is the record.

- A contract can carry a cost code, so the commitment is visible against the project.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Work starts before the contract is signed | There is no agreed scope or price to hold anyone to, and the commitment is invisible to the budget. |

## 6.3 Overview

What it is for. Today's priorities, live project signals and workflow pressure in one place.

### How to operate it

- Start here. My Queue shows what is waiting on you specifically; the rest is context.

## 6.4 Projects and Sites

What it is for. The project and site register — the record everything else hangs off.

### How to operate it

- A site carries its supervisor, client, location and map coordinates.

- Sites have a stage and a status. A site that is closing should say so, because it changes what people expect to see on it.

- Almost every other module keys off the site: budgets, requests, schedules, attendance, reports.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A site is not created before work starts | Requests, attendance and reports have nowhere to attach, and the spend cannot be traced to a project. |

## 6.5 Subcontractors

What it is for. Firms working under the company on a project, and what they are owed.

### How to operate it

- Subcontractor payments notify Finance and the MD, and appear in a Finance queue on the subcontractors screen.

- A subcontractor is a supplier of kind subcontractor or both — the same register.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A payment is agreed off-system | It is not in the budget, not in the ledger and not visible to Finance until somebody remembers. |

## 6.6 Workers

What it is for. Casual and permanent site workers, and their rates.

### How to operate it

- A worker must exist here before attendance can be captured for them.

- Worker type — casual or permanent — decides which payroll engine pays them.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A worker is not registered | They cannot be marked present and will not be paid by the system. |

# 7. Commercial

## 7.1 Interim Payment Certificates, Variations and Claims

What it is for. Interim payment certificates, variations and claims — the commercial position on a contract.

### How it moves

- IPC: draft → submitted → certified → invoiced → paid

- Variation: draft → submitted → priced → approved → closed

- Claim: draft → submitted → under review → agreed → closed

### How to operate it

- A variation is a change to the scope. Price it before seeking approval — an approved variation with no price is an argument waiting to happen.

- Claims are typed: extension of time, loss and expense, acceleration, disruption, prolongation, or variation dispute.

- An IPC becomes an invoice once certified. That is the link between the commercial position and the money.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A variation is instructed but not recorded | The work is done and not paid for. This is the single most expensive omission in the module. |
| An IPC is certified but never invoiced | The certified amount is never billed. |

# 8. Money

## 8.1 Cost Codes and WBS

What it is for. The one key that links what was planned, what was requested, what was committed and what was actually spent.

### How to operate it

- The company library holds 53 approved codes, each mapped to a general ledger account. Finance and the MD control the library.

- A project's own list assembles itself from use: picking a library code provisions it onto the project the first time it is used, under a default General phase.

- Spend always charges a leaf, never a phase. A budget line may sit on a phase, because a phase total is the roll-up of its leaves.

- Code 90.90 is unplanned / contingency, 90.30 is transport, and 95.00 means uncategorised — to be broken down.

- Recoding after approval is allowed and recorded. It is a correction, not a breach.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A record has no cost code | It is invisible to every band, roll-up and variance report at once. Money without a code still exists — it just cannot be reported against anything. |
| Everything charges 90.90 contingency | That is the system telling you the material schedules are empty, not that the work was unplanned. |

## 8.2 Invoices

What it is for. Bills the company issues to its customers.

### How it moves

- Draft

- Sent

- Paid

### How to operate it

- An invoice needs a customer. If the customer is not on the master list, add them first.

- Sending an invoice posts it to the accounts as revenue and a receivable.

- Marking it paid posts the receipt and clears the receivable.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An invoice is left in draft | It is not revenue, not a receivable, and not chased. |
| Payment is received but not recorded | The customer keeps appearing as owing you money. |

# 9. Health, safety and environment

## 9.1 Health, Safety and Environment Compliance

What it is for. Risk assessments, toolbox talks, PPE issue and safety inspections.

### How to operate it

- A risk assessment belongs to the activity, not the site — reuse and revise it rather than rewriting it per job.

- Toolbox talks run planned → completed, and record who attended. The attendance is the evidence.

- PPE issue is tracked per person: issued, then returned.

- Inspections run planned → completed → action required → closed, with findings tracked to closure.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A toolbox talk is held but attendance is not recorded | You cannot show who was briefed, which is the whole point of the record. |
| PPE is issued without recording it | There is no basis for replacement, and no evidence it was provided. |

## 9.2 Incidents and Actions

What it is for. Incidents, near misses and the corrective actions that follow.

### How it moves

- Reported

- Investigating

- Action required

- Closed

### How to operate it

- Report on the day. Types run from near miss and first aid through to lost time, property damage and environmental.

- Severity is low, medium, high or critical, and drives who is notified immediately.

- Every corrective action has an owner and runs open → in progress → completed → verified.

- A near miss is worth reporting precisely because nothing happened. It is the cheapest lesson available.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An incident is not reported | There is no record for the regulator, the insurer, or the next investigation. |
| A corrective action is completed but not verified | Nobody has confirmed it actually works. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| An open corrective action | escalates on the HSE sweep |

## 9.3 Weekly Health, Safety and Environment Report

What it is for. The weekly safety position, compiled for leadership.

### How to operate it

- Compiled from incidents, inspections, talks and actions already recorded. Record during the week and the report writes itself.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| The week's events were not recorded as they happened | The report has to be reconstructed from memory, and it will be wrong. |

# 10. Plant and transport

## 10.1 Equipment

What it is for. Plant and equipment, who has it, and what it costs to run.

### How it moves

- Request: draft → submitted → approved → allocated → closed

### How to operate it

- Equipment is available, allocated, in maintenance, or inactive.

- Ownership matters: company owned, hired, or leased. Hired plant costs money every day it sits idle on a site.

- Fuel logs and maintenance jobs attach to the equipment record.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An allocation is not closed when the plant comes back | It shows as still on site and cannot be allocated elsewhere. |
| Hired plant is not returned promptly | The hire cost continues and nothing in the system objects. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| An equipment request awaiting decision | 2 days |

## 10.2 Fleet and Logistics

What it is for. Vehicle movements and transport requests.

### How it moves

- Draft

- Submitted

- Approved

- Scheduled

- Completed

### How to operate it

- Request types cover staff transport, material delivery and plant movement.

- Scheduling is what tells the driver. An approved request that is never scheduled does not happen.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A request is approved but not scheduled | Nobody is assigned to it and the movement does not take place. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| A transport request awaiting decision | 2 days |

# 11. Records and reference

## 11.1 Documents

What it is for. The company document register, with version control.

### How to operate it

- A document is a group with versions. Uploading a new file supersedes the previous version rather than replacing it.

- Five visibility tiers: public, management, finance, MD-restricted, and private. The owner and the MD can always see their own.

- A document can also be shared with named people, and a direct share beats the visibility tier.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A revision is uploaded as a new document instead of a new version | Two documents claim to be current and the version history is lost. |

## 11.2 Glossary

What it is for. What the system's terms mean.

### How to operate it

- If a word on a screen is unfamiliar, it is defined here rather than guessed at.

## 11.3 Modules

What it is for. Every module, what it does, and whether you can open it.

### How to operate it

- Use it to find a screen you know exists but cannot locate.

## 11.4 Photos

What it is for. Site photographs, tagged by purpose.

### How to operate it

- Tags are progress, delivery and safety. A delivery photo is evidence; tag it as one.

- Photos can be captured offline and sync later.

## 11.5 Settings

What it is for. Your profile, signature and preferences.

### How to operate it

- Your signature is used on documents you sign, so set it before you first need it.

# 12. Reporting

## 12.1 Department Reports

What it is for. The weekly reporting chain from contributor to manager to leadership.

### How it moves

- Contributor draft

- Submitted to manager

- Manager compiles

- To MD / GM

### How to operate it

- Contributors submit theirs; the manager compiles the department report from them.

- Reminders fire on Monday and Tuesday until last week's compiled report exists.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A contributor does not submit | The manager compiles the department's week with a hole in it. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| A department report | 2 days |

# 13. IT

## 13.1 IT Policies & Guides

What it is for. IT policies and how-to guides.

### How to operate it

- Read the acceptable-use and data-protection policies once. They are short and they are binding.

# Where to look when something seems wrong

| Question | Where to look |
| --- | --- |
| “Why is my request stuck?” | Open it — the banner says exactly what is blocking it and what clears it |
| “What is waiting on me?” | Approvals, and My Queue on the Overview |
| “Where has the money gone on this site?” | Project Budgets, then the site's budget |
| “Why does this charge contingency?” | The item's cost code badge — it means no material schedule line matched |
| “Who changed this?” | Activity Log |
| “What does this word mean?” | Glossary |
| “I think I should be able to see X” | Modules — it lists every module and whether you can open it |

The Engineering habits that keep the system honest Finish what you start, on the day you start it. Record the reason when you decline, defer or override something. And if a screen tells you a record is blocked, read the sentence — it names the fix.

This workbook describes the system as it behaves after the August 2026 workflow remediation. Access shown is taken from the system's own role matrix.