PYMBLE CONSTRUCTION LIMITED

Procurement

Operations Workbook

Turning an approved need into goods on site at a price the company agreed, with the evidence to show it.

| For | Procurement Manager · Procurement Officer · Procurement Assistant |
| --- | --- |
| Covers | 35 modules you can open |
| Version | 1.0 |
| Issued | 19 August 2026 |

Internal document. Access shown here is taken from the system's own role matrix.

Contents

To fill in the page numbers: click anywhere in the contents, then press F9.

# 1. How to use this workbook

This is the Procurement edition. It covers only the modules your roles can actually open, so nothing in it is somebody else's job.

## How each module is described

- What it is for — one sentence.

- How it moves — the states a record passes through, where the module is a workflow.

- How to operate it — the instructions.

- What happens if you don't — the consequence of skipping a step. This is the part most people need.

## Two words used precisely

Live — the record is governing something. A live budget controls spend. A draft one does not, no matter what is written on it.

Charged — money has been attached to a specific piece of work. Money that is not charged still exists; it just cannot be reported against anything.

If you take one thing from this workbook Almost every problem in this system comes from a step that was started and not finished — prices attached but never sent, a budget written but never activated, an order approved but never issued. Each of these now shows on a screen. Nothing here asks you to remember anything.

# 2. What your department can open

Your roles can open 35 of the system's 79 modules. Everything else is another department's, and you will not see it in the menu.

Access differs between roles within the department. This table is the definitive list.

| Module | Procurement Manager | Procurement Officer | Procurement Assistant |
| --- | --- | --- | --- |
| Overview | Yes | Yes | Yes |
| Projects and Sites | Yes | Yes | Yes |
| Workers | Yes | Yes | Yes |
| Attendance | Yes | Yes | Yes |
| Approval Rules | Yes | Yes | Yes |
| Approvals | Yes | Yes | Yes |
| Notifications | Yes | Yes | Yes |
| My Conversations | Yes | Yes | Yes |
| Material Schedule | Yes | Yes | Yes |
| Quotations | Yes | Yes | Yes |
| Receivables | Yes | Yes | — |
| Invoices | Yes | Yes | Yes |
| Photos | Yes | Yes | Yes |
| Documents | Yes | Yes | Yes |
| Modules | Yes | Yes | Yes |
| Glossary | Yes | Yes | Yes |
| Settings | Yes | Yes | Yes |
| Daily Site Reports | Yes | — | — |
| Material Requests | Yes | Yes | Yes |
| Suppliers | Yes | Yes | Yes |
| Requisitions and Purchase Orders | Yes | Yes | Yes |
| Stores and Inventory | Yes | Yes | Yes |
| Delivery Exceptions | Yes | Yes | Yes |
| Finance Overview | Yes | Yes | — |
| Cost Codes and WBS | Yes | Yes | — |
| Project Budgets | Yes | Yes | — |
| Payables | Yes | Yes | — |
| Equipment | Yes | Yes | — |
| Fleet and Logistics | Yes | Yes | — |
| Subcontractors | Yes | Yes | Yes |
| Contracts | Yes | Yes | Yes |
| Department Reports | Yes | Yes | Yes |
| Procurement Reports | Yes | Yes | Yes |
| Get IT Help | Yes | Yes | Yes |
| IT Policies & Guides | Yes | Yes | Yes |

If you cannot see something you think you should Access is set per role, and can be adjusted by IT for anything that is not a money or people module. Ask your manager first — the usual answer is that the work belongs to another role.

# 3. Procurement and materials

## 3.1 Material Requests

YOUR DEPARTMENT OWNS THIS

What it is for. Getting materials to a site, with the company knowing what was ordered, what it cost, and which work it was for.

### How it moves

- Draft — Requester builds the request and adds line items

- Submitted — Sent for approval

- Operations approved — Projects Manager, then Operations Manager

- Pricing — Procurement attaches the actual supplier prices

- Priced — Procurement sends it to Finance

- Cost approved — Finance Manager or Accountant approves the money

- Ordered — Procurement raises and issues the purchase order

- Delivered — Requester or site manager confirms the goods arrived

- Closed — Stores, or automatically on full delivery

### How to operate it

- Add every line item before submitting — a request with no lines cannot be submitted.

- Name the supplier on each line. Pick one from the register if they are on it; type the name if they are not.

- You do not need to pick a cost code. The system derives it: your choice first, then the material schedule line the item matches, then the request's budget line, then the site's unplanned / contingency budget.

- Site requests under K25,000 go Projects Manager then Operations Manager. K25,000 and over adds the Managing Director. Office and general requests go to the Operations Manager only.

- If there is no active Projects Manager, the Managing Director covers that step.

- Requests marked IT are confidential and visible only to leadership, IT, Procurement and Finance.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| No supplier is named on any line | The request cannot be sent to Finance. The screen says so from the moment you add items — you do not have to wait until you press Send. |
| The supplier is typed rather than picked from the register | Still blocked, but the cheap fix is to add them to the supplier register. Recording comparison prices also clears it. |
| The request is K1,000,000 or more | Comparison prices are the only way through. Use Record comparison prices on the request itself. |
| No cost code can be derived | The spend charges unplanned / contingency, so it will not appear against the work it was actually for. That usually means the item is not on the site's material schedule. |
| Procurement prices it but never presses Send to Finance | The request sits in Pricing indefinitely. This is the most common way a request goes quiet. |
| Finance approves but nobody raises the purchase order | The money is reserved but never committed. The budget looks more spent than it is, and the site never gets the goods. |
| The purchase order is raised but never issued | Same as above. A draft order is not an order. |
| Delivery is never confirmed | The cost never becomes actual, so it never reaches the accounts. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| Waiting for approval | 2 days |
| Waiting for pricing | 2 days |
| Approved but not ordered (a reservation) | 60 days, or as soon as the needed-by date is 30 days past |

## 3.2 Material Schedule

YOUR DEPARTMENT OWNS THIS

What it is for. The list of everything a project is planned to consume, with quantities. It is what makes planned-versus-actual possible.

### How it moves

- Draft — Quantity Surveyor, Engineer or Projects Manager writes the schedule and its lines

- Pricing pending — Submitted to Procurement

- Priced — Procurement has attached unit rates and transport estimates

- Issued — Locked in — and this is what generates the project budget

### How to operate it

- Give each line a description, unit, quantity and a cost code. The cost code is what lets material requests inherit the right charge.

- Procurement prices the schedule, not Engineering. Engineering owns the quantities; Procurement owns the rates.

- Issuing generates or updates the site's project budget, one budget line per category, inheriting the cost code from the schedule lines it was summed from.

- A revision supersedes the previous schedule rather than deleting it. Categories the revision no longer covers are zeroed, not removed, because spend may already reference them.

- Material requests match against schedules that are priced OR issued, so a schedule still with Procurement already helps requests charge correctly.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| No schedule is created for a site | Every request on that site charges contingency. Variance reporting is impossible — the system can tell you how much was spent but not what on. |
| A schedule is drafted but never priced | Requests can still match against it once priced, but no budget is generated. |
| A schedule is priced but never issued | No project budget is created. Issuing is what generates it. |
| A schedule line has no cost code | Requests matching that line inherit nothing and fall through to contingency. |

## 3.3 Requisitions and Purchase Orders

YOUR DEPARTMENT OWNS THIS

What it is for. Recording the prices you compared, and turning an approved request into a purchase order the supplier can act on.

### How it moves

- Requisition draft — Built from a material request, or from scratch

- Issued / quoted — Prices recorded against the lines

- Awarded — The chosen supplier per line

- Purchase order draft — Created from the requisition, one per supplier

- Approval pending → approved — Where the order needs its own approval

- Issued — The commitment. This is what tells the site the goods are coming

- Partially received → closed — As Stores receipts against it

### How to operate it

- Suppliers are never invited through this system. Procurement gathers prices by phone, WhatsApp, email or counter visit and records what was compared.

- A requisition can be built from a material request at Pricing, Priced, MD review, Approved or Partially ordered. You do not have to wait for approval.

- Issuing a purchase order is a separate, deliberate act from creating it. Creating an order commits nothing; issuing it does.

- Issuing an order records the committed cost against the budget and relieves the reservation the approval took.

- A part-delivery is normal: the request stays on the Procurement queue for a second round rather than closing.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An order is created but never issued | Nothing is committed, nothing is recorded against the budget, and the supplier has no instruction. The request stays open. |
| A requisition is converted but the orders are left as drafts | The material request stays open and correctly so. It advances when an order is actually issued, not before. |
| Comparison prices are not recorded above the tender threshold | The request cannot reach Finance. The threshold is K1,000,000. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| Purchase order waiting to be issued | 1 day |

## 3.4 Suppliers

YOUR DEPARTMENT OWNS THIS

What it is for. The approved register of who the company buys from.

### How to operate it

- A supplier is active, on hold, or archived. Only an active supplier counts as approved to trade with.

- Adding a typed supplier name to the register is what clears the tender gate on a material request below the threshold — it is usually the cheapest fix.

- Record supplier performance events (delivery, quality, commercial, safety, communication, compliance) as they happen. They are worth nothing recalled at year end.

- Suppliers and subcontractors are distinguished by kind: vendor, subcontractor, or both.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A supplier used regularly is never added to the register | Every request naming them is blocked until somebody records comparison prices instead. The register entry is a one-time job; the comparison is per request. |
| A supplier is left active after they should be on hold | Requests naming them pass without the extra check they should get. |

## 3.5 Stores and Inventory

YOUR DEPARTMENT OWNS THIS

What it is for. What the company physically holds, where it is, and what has moved in or out.

### How it moves

- Goods received note — Recorded against a purchase order line when the delivery arrives

- Stock movement — Receipt, issue, transfer or adjustment

- Purchase order closes — Once everything ordered has been received

### How to operate it

- Locations are central store, site store, yard, or vehicle. Every movement is between locations.

- A goods received note is the receipt evidence for a delivery, and the basis of the three-way match between order, receipt and invoice.

- Receipting in full closes the purchase order and the material request behind it.

- An adjustment records a stock count difference — use the reason field, because an unexplained adjustment is indistinguishable from a loss.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| No goods received note is recorded | Delivery is confirmed on somebody's word alone. The three-way match has nothing to work with, and an overcharge on the supplier invoice cannot be caught. |
| Issues to site are not recorded | Stock on hand is overstated, and the site appears not to have received material it is using. |

## 3.6 Delivery Exceptions

YOUR DEPARTMENT OWNS THIS

What it is for. Recording when a delivery was late, short, over, damaged or wrong, so the supplier record reflects it.

### How it moves

- Open

- Investigating

- Resolved

- Closed

### How to operate it

- Raise the exception when the delivery is received, not later. Types are late, short, over, damaged, wrong item, and quality.

- Severity is low, medium, high or critical — it drives who is notified.

- Resolving an exception is a statement that the matter is settled with the supplier, not that time has passed.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Exceptions are not raised | Supplier performance looks perfect on paper. The register cannot tell you who is reliable, which is the only reason to keep it. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| An open exception | 2 days |

## 3.7 Procurement Reports

What it is for. Your department's own weekly report and its history.

### How to operate it

- Write it from what the system already holds rather than from memory — the figures are there.

- The manager compiles the department report from the contributors' submissions.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| The report is skipped | Leadership sees no position for your department that week, and reminders continue on Monday and Tuesday. |

# 4. Your day

## 4.1 Approval Rules

What it is for. The thresholds and chains that decide who approves what.

### How to operate it

- The material request threshold is K25,000 — above it the Managing Director is added as a final step.

- The competitive tender threshold is K1,000,000 — at or above it, recorded comparison prices are the only way through.

- Budget bands: warn at 90%, record-why at 100%, escalate at 110%.

- Raising a threshold can only ever shorten a chain, so change it deliberately.

## 4.2 Approvals

What it is for. Everything waiting for your decision, in one place.

### How to operate it

- An approval has ordered steps. Yours becomes actionable when the steps before it are done.

- A rejection needs a reason. The requester sees it and acts on it.

- Cancelling the underlying record withdraws its approval automatically — you will not be asked to authorise something that no longer exists.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An approval is left sitting | Everything behind it stops. Approvals are flagged as late after 2 days and then escalate. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| Any approval step | 2 days |

## 4.3 Get IT Help

What it is for. Raising an IT problem.

### How to operate it

- Describe what you were doing when it happened. A ticket saying 'it does not work' takes three messages to become useful.

## 4.4 My Conversations

What it is for. Conversations and mentions on records.

### How to operate it

- Mentioning someone notifies them and links them to the record in question.

## 4.5 Notifications

What it is for. What the system needs you to know about.

### How to operate it

- Notifications are deduplicated, so a repeated event updates the existing notice rather than adding another.

- An action link takes you straight to the record.

# 5. Projects and people

## 5.1 Attendance

What it is for. Who was on site, on which day.

### How to operate it

- Pay is a fixed daily rate for each attended day — K60 flat — plus separately entered overtime. Base pay is never scaled by hours worked.

- Presence is present, late, or absent.

- Attendance can be captured in the app or entered manually, and works offline on site.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A day is not captured | That worker is not paid for it. Payroll builds only from what attendance recorded. |

## 5.2 Contracts

What it is for. Works orders and employment contracts, from drafting through signature.

### How it moves

- Draft

- Review

- Approved

- Sent for signature

- Signed / active

- Completed or terminated

### How to operate it

- Contracts are built from a standard template, then every clause can be edited per contract.

- Two template kinds: works order (for a supplier or subcontractor) and employment.

- Signatures are rendered server-side onto the document — the signed PDF is the record.

- A contract can carry a cost code, so the commitment is visible against the project.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Work starts before the contract is signed | There is no agreed scope or price to hold anyone to, and the commitment is invisible to the budget. |

## 5.3 Overview

What it is for. Today's priorities, live project signals and workflow pressure in one place.

### How to operate it

- Start here. My Queue shows what is waiting on you specifically; the rest is context.

## 5.4 Projects and Sites

What it is for. The project and site register — the record everything else hangs off.

### How to operate it

- A site carries its supervisor, client, location and map coordinates.

- Sites have a stage and a status. A site that is closing should say so, because it changes what people expect to see on it.

- Almost every other module keys off the site: budgets, requests, schedules, attendance, reports.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A site is not created before work starts | Requests, attendance and reports have nowhere to attach, and the spend cannot be traced to a project. |

## 5.5 Subcontractors

What it is for. Firms working under the company on a project, and what they are owed.

### How to operate it

- Subcontractor payments notify Finance and the MD, and appear in a Finance queue on the subcontractors screen.

- A subcontractor is a supplier of kind subcontractor or both — the same register.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A payment is agreed off-system | It is not in the budget, not in the ledger and not visible to Finance until somebody remembers. |

## 5.6 Workers

What it is for. Casual and permanent site workers, and their rates.

### How to operate it

- A worker must exist here before attendance can be captured for them.

- Worker type — casual or permanent — decides which payroll engine pays them.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A worker is not registered | They cannot be marked present and will not be paid by the system. |

# 6. Engineering and site control

## 6.1 Daily Site Reports

What it is for. What happened on site each day — progress, labour, plant, materials, delays, safety and commercial events.

### How it moves

- Draft

- Submitted

- Reviewed

- Closed

### How to operate it

- One report per site per day. Entries are typed: progress, labour, equipment, material, delay, HSE, commercial.

- Record delays on the day they happen with the reason. A delay reconstructed weeks later is worth very little in a claim.

- Reports can be written offline and sync when there is signal.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Daily reports are not written | There is no contemporaneous record of delay or disruption. Extension-of-time and loss-and-expense claims depend almost entirely on this. |

# 7. Commercial

## 7.1 Quotations

What it is for. Prices the company offers to customers.

### How it moves

- Draft

- Sent

- Accepted / declined / expired

### How to operate it

- An accepted quotation can be converted into the downstream records rather than retyped.

- Set the expiry. An open-ended quotation is a price you have to honour indefinitely.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A quotation is not marked accepted or declined | The pipeline figure is wrong, and nothing downstream is created. |

# 8. Money

## 8.1 Cost Codes and WBS

What it is for. The one key that links what was planned, what was requested, what was committed and what was actually spent.

### How to operate it

- The company library holds 53 approved codes, each mapped to a general ledger account. Finance and the MD control the library.

- A project's own list assembles itself from use: picking a library code provisions it onto the project the first time it is used, under a default General phase.

- Spend always charges a leaf, never a phase. A budget line may sit on a phase, because a phase total is the roll-up of its leaves.

- Code 90.90 is unplanned / contingency, 90.30 is transport, and 95.00 means uncategorised — to be broken down.

- Recoding after approval is allowed and recorded. It is a correction, not a breach.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A record has no cost code | It is invisible to every band, roll-up and variance report at once. Money without a code still exists — it just cannot be reported against anything. |
| Everything charges 90.90 contingency | That is the system telling you the material schedules are empty, not that the work was unplanned. |

## 8.2 Finance Overview

What it is for. One screen showing where the money is across projects, budgets and the ledger.

### How to operate it

- The Cost subledger and general ledger panel is the integrity check: it compares what operations recorded against what reached the accounts.

- Zero unposted is the healthy state. If it is not zero, use the button beside the number to post the outstanding entries.

- The Reservations awaiting procurement panel shows approved spend nobody has ordered. Anything over 60 days is flagged.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| The unposted count is left non-zero | Operations and the accounts disagree by that amount, and the difference grows quietly. |

## 8.3 Invoices

What it is for. Bills the company issues to its customers.

### How it moves

- Draft

- Sent

- Paid

### How to operate it

- An invoice needs a customer. If the customer is not on the master list, add them first.

- Sending an invoice posts it to the accounts as revenue and a receivable.

- Marking it paid posts the receipt and clears the receivable.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An invoice is left in draft | It is not revenue, not a receivable, and not chased. |
| Payment is received but not recorded | The customer keeps appearing as owing you money. |

## 8.4 Payables

What it is for. Paying suppliers and other bills.

### How it moves

- Draft

- Submitted

- Finance review

- Approved

- Paid

### How to operate it

- Attach the supplier invoice or receipt. A payment request without evidence is a request to trust somebody's memory.

- Marking a request paid is what posts it to the accounts. Paying from the bank without marking it here leaves your payables overstated.

- Loan instalments never come through here — see Loans.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Submitted but never reviewed | It sits. Nothing chases it beyond the flag. |
| Approved but never marked paid | The supplier may have been paid from the bank, but the system still shows it owing. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| Any stage | 2 days |

## 8.5 Project Budgets

What it is for. What a project is allowed to spend, per kind of work, so overspend is visible while it is happening rather than afterwards.

### How it moves

- Draft — A plan somebody is writing. It controls nothing

- Active — Live. This is what spend is measured against. One per site

- Locked — Closed to edits, still measuring

- Archived — Superseded

### How to operate it

- Every budget line needs an amount and a cost code. A line without a cost code cannot be saved, and a budget with one cannot be activated.

- Activating is the moment a plan starts governing. On activation the system links every open request on that site to the budget, codes any uncoded items, and reports what it did.

- Set a contingency amount. Off-schedule spend lands on the contingency leaf by design, and without an allowance there is nothing to measure it against.

- Only one budget can be active per site. Lock or archive the old one before activating a new one.

- A budget can also be generated automatically by issuing a material schedule.

### The spending bands

When Finance approves a cost, the system reports where that leaves the budget.

| Band | When | What happens |
| --- | --- | --- |
| OK | Under 90% used | Approve normally |
| Warning | Over 90% | Shown, no extra step |
| Record why | Over 100% | Approval allowed, but a reason is required. Finance Manager notified |
| Escalate | Over 110%, or no live budget | Approval allowed, and the MD and GM are notified |

Worth knowing Spend is never blocked. It is made visible — blocking a site mid-pour helps nobody. One exception: the contingency line asks for a reason rather than escalating even when unfunded, because off-schedule spend legitimately lands there all day and an escalation that fires on everything is one people learn to ignore.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| The budget is left in draft | Nothing is measured. Every request on that site reports as unfunded, and Finance gets a record-why prompt on every approval. The budget-health panel lists exactly which sites are in this state. |
| A budget line has no cost code | The money on that line is invisible to the availability bands, the roll-up and every variance report. The system refuses to activate the budget and names the lines. |
| No contingency amount is set | You will get record-why on every off-schedule request, indefinitely. |

## 8.6 Receivables

What it is for. What customers owe the company, and how long they have owed it.

### How to operate it

- Ageing is calculated from the invoice date. An invoice with no due date cannot be judged overdue reliably.

- This is a view over invoices — fix a wrong figure on the invoice, not here.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| Invoices are not raised in the system | Receivables shows nothing owing, whatever the reality. |

# 9. Plant and transport

## 9.1 Equipment

What it is for. Plant and equipment, who has it, and what it costs to run.

### How it moves

- Request: draft → submitted → approved → allocated → closed

### How to operate it

- Equipment is available, allocated, in maintenance, or inactive.

- Ownership matters: company owned, hired, or leased. Hired plant costs money every day it sits idle on a site.

- Fuel logs and maintenance jobs attach to the equipment record.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| An allocation is not closed when the plant comes back | It shows as still on site and cannot be allocated elsewhere. |
| Hired plant is not returned promptly | The hire cost continues and nothing in the system objects. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| An equipment request awaiting decision | 2 days |

## 9.2 Fleet and Logistics

What it is for. Vehicle movements and transport requests.

### How it moves

- Draft

- Submitted

- Approved

- Scheduled

- Completed

### How to operate it

- Request types cover staff transport, material delivery and plant movement.

- Scheduling is what tells the driver. An approved request that is never scheduled does not happen.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A request is approved but not scheduled | Nobody is assigned to it and the movement does not take place. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| A transport request awaiting decision | 2 days |

# 10. Records and reference

## 10.1 Documents

What it is for. The company document register, with version control.

### How to operate it

- A document is a group with versions. Uploading a new file supersedes the previous version rather than replacing it.

- Five visibility tiers: public, management, finance, MD-restricted, and private. The owner and the MD can always see their own.

- A document can also be shared with named people, and a direct share beats the visibility tier.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A revision is uploaded as a new document instead of a new version | Two documents claim to be current and the version history is lost. |

## 10.2 Glossary

What it is for. What the system's terms mean.

### How to operate it

- If a word on a screen is unfamiliar, it is defined here rather than guessed at.

## 10.3 Modules

What it is for. Every module, what it does, and whether you can open it.

### How to operate it

- Use it to find a screen you know exists but cannot locate.

## 10.4 Photos

What it is for. Site photographs, tagged by purpose.

### How to operate it

- Tags are progress, delivery and safety. A delivery photo is evidence; tag it as one.

- Photos can be captured offline and sync later.

## 10.5 Settings

What it is for. Your profile, signature and preferences.

### How to operate it

- Your signature is used on documents you sign, so set it before you first need it.

# 11. Reporting

## 11.1 Department Reports

What it is for. The weekly reporting chain from contributor to manager to leadership.

### How it moves

- Contributor draft

- Submitted to manager

- Manager compiles

- To MD / GM

### How to operate it

- Contributors submit theirs; the manager compiles the department report from them.

- Reminders fire on Monday and Tuesday until last week's compiled report exists.

### What happens if you don't

| If this is not done | What happens |
| --- | --- |
| A contributor does not submit | The manager compiles the department's week with a hole in it. |

### When it counts as late

| Stage | Late after |
| --- | --- |
| A department report | 2 days |

# 12. IT

## 12.1 IT Policies & Guides

What it is for. IT policies and how-to guides.

### How to operate it

- Read the acceptable-use and data-protection policies once. They are short and they are binding.

# Where to look when something seems wrong

| Question | Where to look |
| --- | --- |
| “Why is my request stuck?” | Open it — the banner says exactly what is blocking it and what clears it |
| “What is waiting on me?” | Approvals, and My Queue on the Overview |
| “Where has the money gone on this site?” | Project Budgets, then the site's budget |
| “Why does this charge contingency?” | The item's cost code badge — it means no material schedule line matched |
| “Who changed this?” | Activity Log |
| “What does this word mean?” | Glossary |
| “I think I should be able to see X” | Modules — it lists every module and whether you can open it |

The Procurement habits that keep the system honest Finish what you start, on the day you start it. Record the reason when you decline, defer or override something. And if a screen tells you a record is blocked, read the sentence — it names the fix.

This workbook describes the system as it behaves after the August 2026 workflow remediation. Access shown is taken from the system's own role matrix.